## Sheet1
Sprint Project
Task | Tanggal Mulai | Tanggal Selesai | Nama Developer | Status
Preprocessing Data | 2021-10-23 | 2021-10-27 | Lulita | Done
Modelling CNN | 2021-10-23 | 2021-10-27 | Andhika | Done
Augmentasi Data | 2021-11-07 | 2021-11-10 | Lulita | Done
Pretrained Model | 2021-11-20 | 2021-11-24 | Andhika | Done
Augmentasi Random Noise | 2021-12-12 | 2021-12-14 | Lulita | Done
Backend Web | 2021-12-22 | 2021-12-29 | Andhika | Done
Model Deployment | 2021-12-26 | 2021-12-29 | Andhika | Done