## Sheet1
Sprint Project
Task | Tanggal Mulai | Tanggal Selesai | Nama Developer | Status
Preprocessing Data | 2021-10-23 | 2021-10-27 | Lulita | Done
Modelling CNN | 2021-10-23 | 2021-10-27 | Andhika | On Going
Augmentasi Data | 2021-11-07 | 2021-11-10 | Lulita | On Going
Pretrained Model |  |  | Andhika | Waiting
Frontend Web |  |  | Lulita | Waiting
Backend Web |  |  | Lulita | Waiting
Deployment |  |  | Andhika | Waiting
Testing |  |  | Andhika | Waiting